BGCCC 2021 Events Status

RD meeting 5/12/21

1:30-3pm

Attendees: Brian, Duncan, Mckenzie, Karen, Marji, Scott, Julie

1:30-1:35 (5 minutes)

Welcome and Grant Update  										Brian

36k grant renewed called TGYS

Finance Director Started

1:35-1:45 (10 minutes)

Youth of the Year “Week” Review 					               				Cara

Group discussion:

- What went well

  - ~10x more views than what we did in the past

  - Videos are still accessible for continued reach

  - Marji did a great job, sharing article and getting exposure!

- Even better if

  - Chaffee Co times article did not turn out too well

  - Next year have in person plus week before have the highlight videos!

  - Spot to honor youth of the year at the club-salida has a spot-Marji will follow up with brain on this for this year kids

1:45-2:00 (15 minutes)

Drive In Summer Kick-Off

Date: May 27th (Thursday last day of school)

Marketing event to showcase our summer program offering with hopes of growing

membership and knowledge of what the club offers during the summer

| Groups | Program Development Team | Marketing Event Team | Day of Support |
| --- | --- | --- | --- |
| Responsibilities | - Movie preview-filmed - Confirm movie Sing | - Develop marketing plan-see below - Free ticket done | - Ticket Sales - Putting up BGC banner - Running Movie Preview - Welcome announcements |
| Who | Cara/ Brian | Marji Mckenzie |  |

Update:

- Gates open at 7:30pm, movie ~8:50pm

- Marketing plan (Marji)

  - flyer (& where distributed)

  - 4 insertions placed of ad (2 each in MM and CCT)

  - Facebook postings

  - Website

  - Constant contact

  - Will send a second constant contact blast

  - Chamber newsletters (posted on both salida and BV)

  - press release

- Ask Schools if they will hand out flyer or add to their announcements

  - Who: Brain sharing with Jenn and Kiki

- Posters around town:

  - Brian will ask Brandon and Jenn

- Club summer program video

  - Filmed

  - Edit by Greg plan to have draft to Brian and I by Monday

Day of support:

- Laptops

  - Laptop #1 Cara

  - Laptop #2: Julie

  - Laptop #3: mckenzie (Brian to get from her)

- Ticket Sales (1-2 people)

  - Person #1-karen

  - Person #2-Duncan

  - Need to bring square like device-heart of gives to donate now

  - Brian to bring cash bag for change

  - Summer program flyers and Banner (print front and back salida and bv)

  - Cara email barb to get in at 7:15pm

  - Chamber billboard brian will reach out to see if they can add it if not will ask about gala event

2:00-2:15 (15 minutes)

Sponsors       										         	       Team Discussion

Update:

- Review current sponsor status

- Need to schedule “sponsor commercial” filming for Peak sponsors

- What is going well? Any even better if?

| Who | 2019 | 2020 | 2021 |
| --- | --- | --- | --- |
| Buena Vista Veterinary Clinic, Greg & Dale Kettering | $2,500 | $3,000 | $6,000 |
| High Country Bank | $2,500 | $3,000 | $6,000 |
| BURM | $2,500 | $3,000 | $3,000 |
| Elevation Beer Company | $1,000 | $1,250 | $3,000 |
| Heart of the Rockies Regional Medical Center |  | $3,000 | $3,000 |
| Jenna L. Mazzucca, Esq., PC |  | $500 | $3,000 |
| Nestles waters "blue triton brands" | $1,000 | $3,000 | $3,000 |
| Republic National Distributing | $2,500 | $3,000 | $3,000 |
| Salida Pharmacy & Fountain |  |  | $1,250 |
| Brown Dog Coffee Company-BV | $250 |  | $500 |
| Mariposa Window & Door | $250 | $250 | $500 |
| Su Casa! Furniture & Sleep Shop | $500 | GC | $500 |
| Wag-N-Tails | $250 | $250 | $300 |
| The Beekeeper's Honey Boutique |  |  | $200 |
| Mt. Shavano Ski Rental Inc | $150 |  | $100 |
| Total |  |  | $33,350 |

- September 1 deadline for Gala marketing benefits

- Julie will follow up community volunteer on dates needed

  - If not we need to circle back with realtors ourselves

Need to email kiki the title and peak sponsor so it’s on the monitor

2:15-2:25 (10 minutes)

Ribbon Cutting event	    											Julie

Ribbon Cutting Event at Salida Club

- Date: June 12th

- Time: 10am and noon

- What to expect

  - Email constant contact invite list

  - 10 am ribbon cutting then 10:10-11 tours; 11 ribbon to teen or gym; noon next ribbon cutting followed by more tours

  - Snacks

  - We are announcing the capital campaign at this event

July 17th a more private ribbon cutting (invite only)

Need to add the sponosors to the slide show at the salida club

2:25-2:40 (15 minutes)

Stewardship Event										           Team Discussion

Date: July 27th at Surf Hotel (Tuesday)

Invite only Thank you Event

| Groups | Program Development Team | Invite List Team (top 80-100) | Day of Support |
| --- | --- | --- | --- |
| Responsibilities | - Create Content for the program | - Develop the invite list - Save the date - invite | - Event Set up - Event take down - Etc…..more to come |
| who | Julie/Brian | Julie Brian Duncan Karen Subcommittee meeting every Tuesday |  |

Event Logistics Lead: Jeanine

- Will follow up to get official contract confirmed

- Minimum is $50 per person (drinks/aps)

Subcommittee

- Invite list

- Save the date/invitation

- Program content

Ideas:

- Kids call to invite folks

NO PLANS TO DISCUSS UNLESS THERE ARE UPDATES ON 5/11 RD CALL

Joint Event “Great Futures Gala: Let’s Get Back to the Future”

Date: September 28th at Mt Princeton (Tuesday)

Theme: Futuristic (Think Space, Robots, Men in Black, Back to the future 2, Galaxy)

Event Logistics Lead: Jeanine

Needs/Next steps:

- Large auction items: need everyone to brainstorm

  - Julie: timeshare in palm springs or in Mexico

  - Karen: has Conrad Nelson artist for large auction item

- “active” entertainment ideas

  - Happy hour -live painter Joshua Been (tbd)  then auction off painting of the view-Duncan will notify

  - Mentalist Sean Bott CONFIRMED

  - Auctioneer Jim Wilson CONFIRMED

| Groups | Program Development Team | Marketing Event Team | Ticket Sales | Day of Support |
| --- | --- | --- | --- | --- |
| Responsibilities | - Create Content for the program | - Develop marketing plan - Create Ticket | - Develop plan for ticket sales | - Event Set up - Event check in - Event take down - Etc…..more to come |
| Who | TBD |  |  |  |

Tickets: then allow option for additional donation